## Comm. Strategy - Plan 2018 (hidden)
Annual Communication Plan 2018
[10 empty] | February |  |  |  |  | March |  |  |  |  | April | [5 empty] | May |  |  |  |  | June |  |  |  |  | July | [5 empty] | August |  |  |  |  | September |  |  |  |  | October |  |  |  |  | November |  |  |  |  | December
|  | Tool |  | Main Target Audience | How | Date of Implementation | Contribution to the Communication Strategy | Contribution to indicator | Comments | 01-04. | 05-11. | 12-18. | 19-25. | 26-04. |  | 05-11. | 12-18. | 19-25. | 26-01. |  | 02-8. | 09-15. | 16-22. | 23-29. | 30-06. |  | 07-13. | 14-20. | 21-27. | 28-03. |  | 04-10. | 11-17. | 18-24. | 25-01. |  | 02-08. | 09-15. | 16-22. | 23-29. | 30-05. |  | 06-12. | 13-19. | 20-26. | 27-02. |  | 03-09. | 10-16. | 17-23. | 24-30. | 01-07. | 08-14. | 15-21. | 22-28. | 29-04. |  | 05-11. | 12-18. | 19-25. | 26-02. |  | 03-09. | 10-16. | 17-23. | 23-31.
Online communication | I | Programme website | 1 | general public | Publication of news | Continuous (2-3 pcs of news/month) | [6 empty] | Announcing Quiz results |  |  |  |  | Call for Applications + Invitation to Info Day | Results of the CP |  |  | 2nd notification on Info Day | Spring contest announcement | Info Day follow up | Info Day follow up |  | Info Day follow up |  |  |  |  | Reminder on Application Deadline | Spring Contest results + EC DAY (save the date) + Invitation to contract signature + Photo competition announcement | News on contract signature | News on the submitted proposals |  | Invitation to listen to the thematic hours in radio (Priority 2) | [8 empty] | EC DAY 2nd announcement + Invitation to listen to the thematic hours in radio (Priority 1) |  | Reminder on photo submission deadline | Invitation to Reporting WS + News on photo competition submission | Invitation to contract signatues | Call for best project competition + News on EC DAY | News on contract signature |  | Autumn contest announcement + 2nd notification on Reporting WS |  |  |  |  | Reporting WS follow-up | Reminder on autumn contest deadline |  |  |  | Results of the Photo competition and autumn competition | Results of the CP | Season's Greetings
|  |  | 2 |  | Announcing contests | April 2018 October 2018 |  |  | Contests outlines (decision on concepts) by end of February Spring contest concept by end-March Spring contest details to announce (rules, prizes, etc.) by mid-April Autumn contest concept by mid-September Autumn contest details to announce (rules, prizes, etc.) by mid-October Result announcement in June and early December |  |  |  | Contest outlines | [5 empty] | Spring contest concept |  |  |  | Spring contest announcement | [9 empty] | Competition RESULT ANNOUNCEMENT | [14 empty] | 10-16.: Autumn contest concept; October 15-21.: Autumn contest announcement | [6 empty] | Competition RESULT ANNOUNCEMENT | Competition RESULT ANNOUNCEMENT
|  |  | 3 | media | Publication of news | end of March, mid-Q4 June to September/October as occurs |  |  | Results of the CP Official Contract Signature Dates Major events of the CP | [9 empty] | Results of the CP | [12 empty] | Official Contract Signature | Official Contract Signature | Official Contract Signature | [14 empty] | Official Contract Signature | Official Contract Signature | Official Contract Signature | Official Contract Signature | Official Contract Signature | Official Contract Signature | [9 empty] | Results of the CP
|  |  | 4 | programme partners, expert and political public | Publication of news | as occurs end of March end of June |  |  | Major events of the CP Results of the CP Official Contract Signature Dates | [9 empty] | Results of the CP | [12 empty] | Official Contract Signature | Official Contract Signature | Official Contract Signature | [14 empty] | Official Contract Signature | Official Contract Signature | Official Contract Signature | Official Contract Signature | Official Contract Signature | Official Contract Signature | [9 empty] | Results of the CP
|  |  | 5 | (potential) beneficiaries | Publication of news | as occurs March end of March, mid-Q4 June to September/October September/October (?) |  |  | Major events of the CP Call for Applications - deadline Results of the CP Official Contract Signature Dates Call for "Best Practice" project competition | [8 empty] | Call for Applications | Results of the CP | [12 empty] | Official Contract Signature | Official Contract Signature | Official Contract Signature | [14 empty] | Official Contract Signature | Official Contract Signature | Official Contract Signature + Call for "Best Practice" project competition | Official Contract Signature + Call for "Best Practice" project competition | Official Contract Signature | Official Contract Signature | [9 empty] | Results of the CP
| II | Social media (networks) | 6 | general public (young people) | Publication of news/ announcing photo competition | Continuous |  |  | Photo competition concept by May Concept details (rules, prizes, etc.) and announcement by mid-June Submission of photos by mid-September Ceremony in the course of an official contract signature date | [17 empty] | Photo competition concept | [5 empty] | Photo competition announcement | [14 empty] | 10-16.: Submission of photos for competition | [6 empty] | Result announcement (Photo competition) | Result announcement (Photo competition)
|  |  | 7 |  | Announcing contests | April 2018 October 2018 |  |  | Contests outlines (decision on concepts) by end of February Spring contest concept by mid-March Spring contest details to announce (rules, prizes, etc.) by mid-April Autumn contest concept by mid-September Autumn contest details to announce (rules, prizes, etc.) by mid-October |  |  |  | Contest outlines | [5 empty] | Spring contest concept |  |  |  | Spring contest announcement | [9 empty] | Competition RESULT ANNOUNCEMENT | [14 empty] | 10-16.: Autumn contest concept; October 15-21.: Autumn contest announcement | [6 empty] | Competition RESULT ANNOUNCEMENT | Competition RESULT ANNOUNCEMENT
|  |  | 8 | media | Publication of news | end of March, mid-Q4 June to September/October as occurs |  |  | Results of the CP Official Contract Signature Dates Major events of the CP | [9 empty] | Results of the CP | [12 empty] | Official Contract Signature | Official Contract Signature | Official Contract Signature | [14 empty] | Official Contract Signature | Official Contract Signature | Official Contract Signature | Official Contract Signature | Official Contract Signature | Official Contract Signature | [9 empty] | Results of the CP
|  |  | 9 | programme partners, expert and political public | Publication of news | as occurs end of March end of June |  |  | Major events of the CP Results of the CP Official Contract Signature Dates | [9 empty] | Results of the CP | [12 empty] | Official Contract Signature | Official Contract Signature | Official Contract Signature | [14 empty] | Official Contract Signature | Official Contract Signature | Official Contract Signature | Official Contract Signature | Official Contract Signature | Official Contract Signature | [9 empty] | Results of the CP
|  |  | 10 | (potential) beneficiaries | Publication of news | as occurs March end of March, mid-Q4 June to September/October September (?) |  |  | Major events of the CP Call for Applications - deadline Results of the CP Official Contract Signature Dates Call for "Best Practice" project competition | [8 empty] | Call for Applications | Results of the CP | [12 empty] | Official Contract Signature | Official Contract Signature | Official Contract Signature | [14 empty] | Official contract signature | Official contract signature | Official Contract Signature + Call for "Best Practice" project competition | Official Contract Signature + Call for "Best Practice" project competition | Official contract signature | Official contract signature | [9 empty] | Results of the CP
Direct communication | III | Conferences | 11 | programme partners, expert and political public | Not applicable in 2018 | Not applicable in 2018 | Not applicable in 2018 | Not applicable in 2018 | Not applicable in 2018 | Not Applicable in 2018
|  |  | 12 | (potential) beneficiaries | Not applicable in 2018 | Not applicable in 2018 | Not applicable in 2018 | Not applicable in 2018 | Not applicable in 2018 | Not Applicable in 2018
| IV | Seminars / Workshops | 13 | (potential) beneficiaries | Reporting, Controls | November (?) |  |  | Potential topics: Various types of reports To do and not to do when reporting What is checked by JS monitoring visits Get prepared for final reporting | [38 empty] | 10-16.: Notification on WS/Seminar; October 15-21.: 2nd Notification on WS/Seminar; October 29-04.: Registration deadline |  | WS / Seminar on Reporting/Controls | WS / Seminar on Reporting/Controls | WS / Seminar on Reporting/Controls
|  |  | 14 |  | Information day | end of April-mid-May |  |  | Information on the application process Intervention logic - case study? Best practice? | [8 empty] | Notification on Info Day |  |  |  | 2nd notification on Info Day | Registration deadline to Info Day | Info Day | Info Day |  | Info Day
| V | Individual consultations | 15 | (potential) beneficiaries | Face-to-face meetings | Continuous - upon request
| VI | Events for the general public | 16 | general public | EC DAY 2018 | September 2018 |  |  | 1 large by the CP or several smaller by projects? To be announced 1. in mid-June (date); 2. end of August-beginning of September (date + location + proposed agenda + registration <??>); 3. Final reminder 2 days prior to the event | [13 empty] | EC DAY 2018 Decision: 1 large by the CP or several smaller by projects? | [9 empty] | EC DAY 2018 to be announced (Save the date) | [12 empty] | EC DAY 2018 to announce: date + location + proposed agenda + open registration |  | 24-30.: EC DAY 2018 to send final reminder 2 days prior to the event + Implementation; October 01-07.: EC DAY 2018 follow up (news, press release)
Communication with media and PR | VII | Press conference | 17 | media | Linked to official CP events | June (and October <?>) December |  |  | At the Official Contract Signature Date(s) max. 2 Announcement of contest results (1 or 2) | [22 empty] | Press Conference linked to Official Contract Signature | Press Conference linked to Official Contract Signature | Press Conference linked to Official Contract Signature | [28 empty] | Press conference on Contest results, Results of the CP, etc. | Press conference on Contest results, Results of the CP, etc.
| VIII | Press release | 18 | media | Linked to official CP events | June to September/October September September/October |  |  | At the Official Contract Signature Date(s) max. 2 EC DAY 2018 Announcement of contest results (1 or 2) | [22 empty] | Press release on official contract signature | Press release on official contract signature | Press release on official contract signature | [28 empty] | Press release on Contest results, CP results, etc. | Press release on Contest results, CP results, etc.
| IX | Media relations | 19 | media (thematic) | Press breakfast? | April 2018 |  |  | Announcing the CP events | [9 empty] | Press breakfast: Announcing contests, EC DAY dates, CP results so far
Media communications | X | Press advertising | 20 | general public | Contests | April 2018 October 2018 |  |  | Invitation to participate in the contests | [13 empty] | Press advertising: Invitation to Spring contest | [9 empty] | Press advertising: Invitation to Photo competition, results of Spring contest | [14 empty] | October 15-21.: Press advertising: Invitation to autumn contest | [7 empty] | ??? Press advertising: results of autumn contest
|  |  | 21 | (potential) beneficiaries | Dates of Seminars / Workshops | end of April-mid-May |  |  | Invitations to workshops / seminars (pls note that press advertising of reporting ws is replaced by direct invitation) | [9 empty] | Press advertising: Invitation to Info Day
| XI | Radio | 22 | general public | Thematic hours | early July late August/start of Sept |  |  | 2 occasions (1 per priority) MAYBE: Short messages followed by questions (Awards?) | [27 empty] | Thematic hours, success stories - Priority 2 | [8 empty] | Thematic hours, Success stories - Priority 1
|  |  | 23 | (potential) beneficiaries | Thematic hours | early July late August/start of Sept | [30 empty] | Thematic hours, success stories - Priority 2 | [8 empty] | Thematic hours, Success stories - Priority 1
| XII | Television | 24 | general public | Layman interviews | at EC Day? |  |  | ?? TV spot: why did I participate in the SIHU EC Day? | [38 empty] | 24-30.: TV spot: Why did I participate in the SIHU EC Day?
|  |  | 25 | (potential) beneficiaries | interviews with beneficiaries | June Sept-Oct |  |  | Linked to official contract signature dates | [22 empty] | TV interviews linked to Official Contract Signature | TV interviews linked to Official Contract Signature | TV interviews linked to Official Contract Signature | [14 empty] | TV interviews linked to Official Contract Signature | TV interviews linked to Official Contract Signature | TV interviews linked to Official Contract Signature | TV interviews linked to Official Contract Signature | TV interviews linked to Official Contract Signature | TV interviews linked to Official Contract Signature
| XIII | Outdoor campaigns | 26 | general public (locals) | EC DAY 2018 | September 2018 |  |  | See Comment to 16 | [13 empty] | EC DAY 2018 Decision: 1 large by the CP or several smaller by projects? | [9 empty] | EC DAY 2018 to be announced (Save the date) | [12 empty] | EC DAY 2018 to announce: date + location + proposed agenda + open registration |  | 24-30.: EC DAY 2018 to send final reminder 2 days prior to the event + Implementation; October 01-07.: EC DAY 2018 follow up (news, press release)
Printed communication tools | XIV | Publications | 27 | (potential) beneficiaries | As per proposals | As per proposals |  |  | As per proposals | As per set in proposals
| XV | Leaflets, posters | 28 | (potential) beneficiaries | As per proposals | As per proposals |  |  | As per proposals | As per set in proposals
Other tools | XVI | Contests | 29 | general public | See above | See above |  |  | See above | Please refer to Rows 2, 5, 6, 7 and 10
| XVII | Promotional items | 30 | general public | Already available | Already available |  |  | Already available | Already available and applied
|  |  | 31 | (potential) beneficiaries | Already available | Already available |  |  | Already available | Already available and applied
| XVIII | Uniform visual identity | 32 | programme partners, expert and political public | Already available | Already available |  |  | Already available | Already available and applied
|  |  | 33 | (potential) beneficiaries | Already available | Already available |  |  | Already available | Already available and applied

## SIHU Comm Plan 2020 (hidden)
SIHU Annual Communication Plan - 2020
Tool | Applied method | Topic | Date | Target
Programme website and Social media (networks) | Publication of news | All information (CP and project related) | All year (average 2-3 per month) | All
|  | Major events (invitation, follow up) | All year
|  | Results of the CP, including projects | Q2/Q3
|  | Contract Signatory Dates | Q2/Q3
| Storytelling | Stories of projects linked to cycling (1-2 stories) | Q2-Q3-Q4
| Publication of news | Publishing entries of photo competition | Q4 | General public | Promoting the results, benefits and best practices of the CP Interreg SI-HU in the period 2014-2020: In
|  | Reminder on Best practice (project) contest | Q2/Q3 (results in 2020-22) | (Potential) beneficiaries | Awerness about EU funded cross-border projects
Seminars / Workshops | Workshop | Reporting and control, project closure | Q3/Q4 | (Potential) beneficiaries | Recognisability of the CP Interreg SIHU
Individual consultations | Personal, on-line | Application, eligibility | All year (upon request of beneficiaries) | (Potential) beneficiaries | Knowledge of the programme website
Events for the general public | Annual event | EC DAY 2020 | September | All
Press conference | Linked to official CP events | Contract Signatory Ceremonies | Q2/Q3 | Media
(Potential) beneficiaries
Press release | Linked to official CP events | Contract Signatory Ceremonies | Q2/Q3 | Media
|  | EC DAY 2020 | September
Media relations | Press conference | Contract Signatory Ceremonies | Q2/Q3 | Media
| Press release | Contract Signatory Ceremonies | Q2/Q3
|  | EC DAY 2020 (follow-up) | September - early October
Press advertising | Annual event | EC DAY 2020 | September | General public
Radio | Linked to official CP events | Contract Signatory Ceremonies | Q2/Q3 | General public
Television | Linked to official CP events | Contract Signatory Ceremonies | Q2/Q3 | General public
|  | EC DAY 2019 (on-site report) | September
Outdoor campaigns | Annual event | EC DAY 2020 | September | All
Contests | Target group oriented contest | Photo competition entries | Q4 | General public
|  | Reminder on Best practice (project) contest | Q2/Q3 (results in 2020-22) | (Potential) beneficiaries

## IP SIHU Comminication Plan 2025
IP SI-HU Annual Communication Plan - 2025
Annual objective | Communication Tool | Topic | Target group(s) | Implementing period | Indicator
Communication and visibility support for standard and small-scale projects under implementation. Informing and motivating potential beneficiaries to elaborate and submit quality applications for the available funds. Also, informing the general public about the results achieved by the programme and the projects so far. | Programme website | The programme website will be used throughout the whole programme period as the basic and at the same time main communication tool for the dissemination of information on the programme in accordance with the CPR. It contains information on activities and events, the Open Calls, responses to FAQs, links to websites of other programmes and programmes relevant contacts. All information provided will be available in the two Member State languages and additionally also in English. The website will be the main platform for presenting projects and their activities and achievements, partly by creating project sub-pages for standard projects and partly by providing news and newsletters on small-scale and standard projects. | All | All year | Number of visitors (users) to the programme website (COMM OI 2.1.)
| Social media | Promotion of the programme's possibilities and projects' activities, achievements. | All | All year | Number of likes/followers on social media (Facebook) (COMM OI 2.3.)
Number of posts published (COMM OI 2.4.)
| Online campaings | Promoting the events and results of small-scale projects. | General public | All year | n.r.
| Seminars and workshops | Seminars and workshops to provide specific information on the content of the IP, Open Calls for Proposals and Manual for Beneficiaries. | (Potential) beneficiaries | Q1-Q2-Q3-Q4 | Number of participants at workshops (COMM OI 1.4.)
Satisfaction with the provided information, guidelines, presentation, support, etc. (COMM RI 1.1.)
| Individual consultations | For potential beneficiaries of projects for period 2021–2027 to provide support for project implementation. | (Potential) beneficiaries | All year (upon request of beneficiaries) | Number of received applications (COMM OI 1.2.)
|  | Individual consultations in the form of face-to-face meetings are organized for the beneficiaries of approved projects to provide additional support for the project implementation | Project partners | Q1-Q2-Q3-Q4 | Number of approved applications (COMM OI 1.3.)
| Informational thematic and networking events | Informational thematic and networking events will be organised in the frame of the programme and between programmes to exchange information on certain topics. | Programme partners | All year | n.r.
| Events for the general public | Interreg Cooperation Day 2025 | All | September | Number of events other than workshops (annual event) (COMM OI 2.5.)
Number of participants at events other than workshops (annual event) (COMM OI 2.6.)
| Press conference | Workshops | Media | Q2-Q3-Q4 | n.r.
|  | Interreg Cooperation Day 2025 |  | September | n.r.
| Media relations | Workshops | Media | Q2-Q3-Q4 | n.r.
|  | Interreg Cooperation Day 2025 |  | September | n.r.
| Television / Radio | Workshops | Media | Q2-Q3-Q4 | n.r.
|  | Interreg Cooperation Day 2025 |  | September | n.r.
| Outdoor campaigns | Interreg Cooperation Day 2025 | All | September | n.r.
| Internet | While the programme website (www.si-hu.eu) and the single website portal (www.evroskasredstva.si) are the most frequent forms of utilisation, the websites of the programme and Project Partners and the EC networks is used for distributing general information to the public. | All | All year | n.r.
| Publications | Contains an overview of all projects implemented in the frame of programme for the period 2014-2020 together with information on the disbursed funding, main project results and highlighted good practices. | All | Q1 | n.r.
| E-newsletter | The e-news of the programme are prepared periodically and distributed electronically via e-mail and the e-newsletter tool on the website to all people who subscribe to receiving the e-news. | Project partners, Programme partners, General public | All year | Level of engagement in the programme newsletter - number of e-newsletters subscibers (COMM OI 2.2.)
| (Online) Contests | The programme animates the target audiences to share the added value of projects and the programme (e.g. through photo and/or other contests) with the general public and, therefore, make the programme and project results more widely known. | Project partners, General public | All year | n.r.
| Promotional items | The items are subject to branding using the uniform visual identity of the programme. | Project partners, Programme partners, General public | All year | n.r.
| Uniformal visual identity | The uniform visual identity is used for all programme documents (the IP, manuals, invitations, brochures, etc.), on the programme website, on the programme's Facebook page, on promotional materials, in the frame of events (invitations, presentations, roll-ups, posters, etc.) in the communication with target audiences (e-mails, official letters, etc.) and other related activities. All Project Partners are obliged to use the uniform visual identity (programme logo/project logo) following the Communication and Visibility guidelines of the programme. | All | All year | n.r.

## Version 2 - SIHU Comm Plan (hidden)
SIHU Annual Communication Plan - 2019
Topic | Applied method | Tool | Date | Target
Stories of projects linked to cycling (1-2 stories) | Storytelling | Programme website and Social media (networks) | Q2-Q3-Q4 | All
Publishing entries of photo competition | Publication of news | Programme website and Social media (networks) | Q4 | General public
Photo competition entries | Target group oriented contest | Contests | Q4 | General public
Reminder on Best practice (project) contest | Target group oriented contest | Contests | Q2/Q3 (results in 2020-22) | (Potential) beneficiaries
Reminder on Best practice (project) contest | Publication of news | Programme website and Social media (networks) | Q2/Q3 (results in 2020-22) | (Potential) beneficiaries
All information (CP and project related) | Publication of news | Programme website and Social media (networks) | All year (average 2-3 per month) | All
Major events (invitation, follow up) | Publication of news | Programme website and Social media (networks) | All year | All
Results of the CP | Publication of news | Programme website and Social media (networks) | Q2/Q3 | All
Contract Signatory Dates | Publication of news | Programme website and Social media (networks) | Q2/Q3 | All
Application, eligibility | Personal, on-line | Individual consultations | All year (upon request of beneficiaries) | (Potential) beneficiaries
Reporting and control, project closure | Workshop | Seminars / Workshops | Q3/Q4 | (Potential) beneficiaries
EC DAY 2019 | Annual event | Events for the general public | September | All
EC DAY 2019 | Annual event | Press advertising | September | General public
EC DAY 2019 | Annual event | Outdoor campaigns | September | All
EC DAY 2019 | Linked to official CP events | Press release | September | Media
EC DAY 2019 (on-site report) | Linked to official CP events | Television | September | General public
EC DAY 2019 (follow-up) | Press release | Media relations | September - early October | Media
Contract Signatory Ceremonies | Linked to official CP events | Press conference | Q2/Q3 | Media
Contract Signatory Ceremonies | Linked to official CP events | Press conference | Q2/Q3 | (Potential) beneficiaries
Contract Signatory Ceremonies | Linked to official CP events | Press release | Q2/Q3 | Media
Contract Signatory Ceremonies | Press conference | Media relations | Q2/Q3 | Media
Contract Signatory Ceremonies | Press release | Media relations | Q2/Q3 | Media
Contract Signatory Ceremonies | Linked to official CP events | Radio | Q2/Q3 | General public
Contract Signatory Ceremonies | Linked to official CP events | Television | Q2/Q3 | General public

## Version 2 - SIHU Comm Plan (2) (hidden)
SIHU Annual Communication Plan - 2019
Topic | Applied method | Tool | Date | Target
Stories of projects linked to cycling (1-2 stories) | Storytelling | Programme website and Social media (networks) | Q2-Q3-Q4 | All
Publishing entries of photo competition | Publication of news |  | Q4 | General public
| Target group oriented contest | Contests
Reminder on Best practice (project) contest |  |  | Q2/Q3 (results in 2020-22) | (Potential) beneficiaries
| Publication of news | Programme website and Social media (networks)
All information (CP and project related) |  |  | All year (average 2-3 per month) | All
Major events (invitation, follow up) |  |  | All year
Results of the CP |  |  | Q2/Q3
Contract Signatory Dates
Application, eligibility | Personal, on-line | Individual consultations | All year (upon request of beneficiaries) | (Potential) beneficiaries
Reporting and control, project closure | Workshop | Seminars / Workshops | Q3/Q4
EC DAY 2019 | Annual event | Events for the general public | September | All
|  | Press advertising |  | General public
|  | Outdoor campaigns |  | All
| Linked to official CP events | Press release |  | Media
EC DAY 2019 (on-site report) |  | Television |  | General public
EC DAY 2019 (follow-up) | Press release | Media relations | September - early October | Media
Contract Signatory Ceremonies | Linked to official CP events | Press conference | Q2/Q3
(Potential) beneficiaries
|  | Press release |  | Media
| Press conference | Media relations
Press release
| Linked to official CP events | Radio |  | General public
Television