## Slide 1: Update on Programme Implementation CP Interreg V-A SI-HU
Aleš Mrkela, Programme manager
Managing Authority,
Moravske Toplice, 5.7.2017

## Slide 2: Some conclusions from 4th MC
MC members were informed regarding the status of the closure of the OP SI-HU 2007-2013 – Closure documents were submitted in March 2017
MC members were informed regarding the status of the designation procedure - Designation has been done in March 2017 (some issues were outlined which will have to be addressed in future versions of Manuals)
Projects were confirmed and new deadline has been set on 11th of April 2017

## Slide 3: Programme activities (1)
Individual Consultations/Meetings with potential applicants
Submission of the Closure documents (FIR, etc.) for 2007-2013 (29 March 2017)
Sent Recoveries for Irregularities found by AA for OP SI-HU 2007-2013
Positive opinion on designation of MA/CA received on 8th March 2017
Evaluation of the 1st and 2nd deadline for submission, including the application procedure
On-going updates of the eMS and the programme website
First Applications for Payment sent to CA, request from EC expected July 2017
Administrative and Quality Assessment of projects in April‘s deadline
eMS workshop for Auditors May 2017
Reporting workshop for Beneficiaries and potential applicants (June 2017)

## Slide 4: Programme activities (2)
On-going:
Checking of the Partner Progress Reports and Lead partners Progress Reports – sending them to CA and EC
Signature of contracts
Workshop for potential applicants (2nd Priority)
Updates of the Programme manuals (Autumn 2017)
Preparation of remaining manuals (e.g. closure and archiving)
Annual programme event (EC Day …) - in autumn (23rd September)

## Slide 5: IAB recommendations - Designation
Link between eMS and Payment service of CA
Risk assessment exercise and manuals shall be updated
Manual on verification and validation of expendicure shall include exact days need for checking the reports
Storage format of files in electronic system should be defined in PDF/A standard
Staff capacity of SI FLC shall be adequate (update of risk assessment)
SI FLC has to have risk assessment for Sampling of expenditure in costs related to equipment and infrastructure

## Slide 6: Open irregularites (financial liability)
AC (Martineum) – LP paid back ERDF but is unable to recover funds from PP (24.160,67 EUR ERDF)
Pannon pleasure
  LP (Občina Lendava) did not pay back total ERDF, just partly - 24.037,31 EUR ERDF remains open
  PP (Skanzen) did not pay back - 15.663,48 EUR ERDF
OP SI-HU 2007-2013

## Slide 7
PRIORITY | PLANNED ERDF | REALISED ERDF | PLANNED NATIONAL CO- FINANCING | REALISED NATIONAL CO- FINANCING | PLANNED TOTAL | REALISED TOTAL
1 - ATTRACTIVE REGION | 10.000.000,00 | 0,00 | 1.764.705,89 | 0,00 | 11.764.705,89 | 0,00
2 – COOPERATIVE REGION | 3.295.015,00 | 0,00 | 581.473,24 | 0,00 | 3.876.488,24 | 0,00
3- TECHNICAL ASSISTANCE | 1.500.000,00 | 3.762,50 | 1.500.000,00 | 3.762,51 | 3.000.000,00 | 7.525,01
TOTAL | 14.795.015,00 | 3.762,50 | 3.846.179,13 | 3.762,51 | 18.641.194,13 | 7.525,01
% | 100 | 0,03 | 100 | 0,09 | 100 | 0,04

## Slide 8
Expenditures situation
36 reports submitted by PPs to FLC
170.144,44 EUR ERDF funds requested by PPs
19 reports submitted but not certified
7.506,32 EUR ERDF not certified, expenditure excluded – sitting duck or ineligible
101.824,26 EUR ERDF funds certified by FLC
5 reports sent to CA
1 report by JS
Prefinancing trouble
Late signature of contracts (national ones)
Slow public procurement
New system slow checking (learning curve)

## Slide 9
Calendar year | ERDF allocation (Table 15 of OP) | N+3 | Deduct initial pre-financing 3% | Deduct annual pre-financing 3% | Calendar year (N+3) = total must be claimed form COM by 31 December | (N+3) cumulative | (N+3) corrected
2014 | 0,00 |  |  |  |  |  | 
2015 | 1.805.355,00 |  |  |  |  |  | 
2016 | 1.530.187,00 |  |  |  |  |  | 
2017 | 2.780.340,00 |  |  |  |  |  | 
2018 | 2.835.947,00 | 1.805.355,00 | -443.850,45 | -1.091.132,36 | 270.372,19 | 270.372,19 | 566.272,49
2019 | 2.892.666,00 | 1.530.187,00 |  | -425.356,68 | 1.104.830,32 | 1.375.202,51 | 
2020 | 2.950.520,00 | 2.780.340,00 |  | -443.850,45 | 2.336.489,55 | 3.711.692,06 | 
2021 |  | 2.835.947,00 |  | -443.850,45 | 2.392.096,55 | 6.103.788,61 | 
2022 |  | 2.892.666,00 |  | -443.850,45 | 2.448.815,55 | 8.552.604,16 | 
2023 (2024) |  | 2.950.520,00 | 443.850,45 | 2.848.040,39 | 6.242.410,84 | 14.795.015,00 | 
TOTAL | 14.795.015,00 | 14.795.015,00 |  |  | 14.795.015,00 |  | 

## Slide 10: Underspending of projects
Projects underspending after 2 consecutive periods (not reaching 85%) – e.g. Green Exercise spent 63%
High risk of de-commitment, especially if we cut funds, due to the lack of projects in pipeline (quality issue)
Proposal is to grant MA right to open interim reports with clear spending profile (especially within one calendar year for reaching N+3 targets)

## Slide 11: 20% Outside eligible area
There are many organizations that have seat outside eligible area, but branches in eligible area (costs are paid from main seat e.g. Schools, Universities, NIF,…)
20% outside eligible area in confirmed projects amount already to:
  Including TA: 3.392.588,66 EUR ERDF,
  Excluded TA: 1.892.558,66 EUR ERDF
  Excluded NIF: 32.704,65 EUR ERDF
Proposal: Accorting to Regulation 1299/2013 art.20.3, the MC members decide that technical assistance is not calculated in 20% outside area and that costs that occur in projects that are for the benefit of the eligible area and where partners have main site outside eligible area due to national legislation shell not be considered as occurred outside eligible area.

## Slide 12: THANK YOU FOR YOUR ATTENTION
QUESTIONS
QUESTIONS?